## Sheet1
# | Task Name | Task Description | Start | End | Duration | Week 9/12 | [6 empty] | Week 9/19 | [6 empty] | Week 9/26 | [6 empty] | Week 10/3 | [6 empty] | Week 10/10 | [6 empty] | Week 10/17 | [6 empty] | Week 10/24 | [6 empty] | Week 10/31 | [6 empty] | Week 11/7 | [6 empty] | Week 11/14 | [6 empty] | Week 11/21 | [6 empty] | Week 11/28 | [6 empty] | Week 12/5 | [6 empty] | Week 12/12 | [6 empty] | Week 12/19 | [6 empty] | Week 12/26 | [6 empty] | Week 1/2 | [6 empty] | Week 1/9 | [6 empty] | Week 1/16 | [6 empty] | Week 1/23 | [6 empty] | Week 1/30 | [6 empty] | Week 2/6 | [6 empty] | Week 2/13 | [6 empty] | Week 2/20 | [6 empty] | Week 2/27 | [6 empty] | Week 3/6 | [6 empty] | Week 3/13 | [6 empty] | Week 3/20 | [6 empty] | Week 3/27 | [6 empty] | Week 4/3 | [6 empty] | Week 4/10 | [6 empty] | Week 4/17 | [6 empty] | Week 4/24
[6 empty] | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
A | IoT Climate System |  | 2022-09-15 | 2022-04-27 | 224 Days
1 | Sensors | Developing a sensor system consisting of various climate sensors with wireless communication | bar: Week 9/19 S to Week 11/7 T; Week 1/16 S to Week 3/6 W
| Research Sensors | Research what types of sensors that we need and what is the most affordable and fit with solar panels | 2022-09-25 | 2022-10-07 | 12 | bar: Week 9/19 S to Week 10/3 F
| Create Sensor Excel Analysis Sheet | Create a list of our researched sensors and design a decision matrix to choose which sensors we want based on cost, compatibility with our proposed system and other important factors | 2022-10-08 | 2022-10-23 | 15 | bar: Week 10/3 S to Week 10/17 S
| Finalize Sensors List | Determine set of sensors to be used in project | 2022-10-24 | 2022-11-19 | 26 | bar: Week 10/24 M to Week 10/31 M
| Submit Datasheets and Sensor Report to Advisors | From the list of finalized sensors, organize and submit all data sheets and sensor data to advisors | 2022-10-28 | 2022-11-19 | 22 | bar: Week 10/31 M to Week 10/31 F
| Begin Ordering Sensors | Organize, and budget out the necessary type and amount of sensors needed for the project | 2022-11-29 | 2022-12-01 | 2 | bar: Week 10/31 S to Week 11/7 M
| Finalize Ordering Sensors | Organize, and budget out the necessary type and amount of sensors needed for the project | 2023-12-21 | 2023-12-29 | 8 | bar: Week 1/16 S to Week 1/23 S
| Create Sensor Layout Plan/Field Testing | Show on a drawing of the site where the sensors and each type of sensor should be places and their relative positioning | 2023-01-30 | 2023-03-08 | 37 | bar: Week 1/30 M to Week 3/6 W
2 | Wireless Communication | bar: Week 10/24 M to Week 11/7 S
| Determine Specification of Wireless Communication | Research wireless communication options aviable, range required, power requirements, and other related project specs | 2022-10-24 | 2022-10-31 | 7 | bar: Week 10/24 M to Week 10/31 M
| Create Excel Sheet of possible options | Compile list of researched modules and wireless communication options | 2022-10-31 | 2022-11-07 | 7 | bar: Week 10/31 M to Week 11/7 M
| Finalize Wireless Communication Module | Determine wireless communication to be used | 2022-11-07 | 2022-11-13 | 6 | bar: Week 11/7 M to Week 11/7 S
3 | Microcontroller | Purchase a microcontroller that is compatble with our sensors, it based on programming that we know or can learn, and can communicate with the app we will develop | bar: Week 10/3 F to Week 10/17 F
| Research Microcontroller | Research microcontrollers that work with our sensor list and can communicate with the app | 2022-10-07 | 2022-10-14 | 7 | bar: Week 10/3 F to Week 10/10 F
| Create microcontroller analysis sheet | Like the sensor sheet, compare the researched microcontrollers to see which option is the best | 2022-10-14 | 2022-10-21 | 7 | bar: Week 10/10 F to Week 10/17 F; Week 1/16 S to Week 3/6 M
| Order Microcontroller | Purchase the microcontroller | 2022-10-22 | 2022-10-29 | 7 | bar: Week 1/16 S to Week 1/23 S
| Power and program microcontroller | Once the microcontroller has been bought, we will begin to make sure the microcontroller has a proper power supply and can be programmed to recieve inputs and outputs | 2022-10-30 | 2022-11-10 | 10 | bar: Week 1/23 S to Week 2/6 R
| Connect and test sensors | Wire up the sensors to the microcontroller and test how the sensor work and display data | 2022-11-10 | 2022-11-19 | 9 | bar: Week 2/6 F to Week 2/13 S
| Test Compatiability with Software Application | Test to see interaction between microcontroller and the software application | 2022-11-20 | 2022-11-27 | 7 | bar: Week 2/13 S to Week 2/20 S
| Connect device to the wireless network | Test devices capability to function in the wireless network provided | 2022-11-27 | 2022-12-05 | 8 | bar: Week 2/20 S to Week 3/6 M
4 | Software Application | Developing a software program (e.g. LabVIEW or a phone app) that collects sensing data from the sensor system and displays the graphs real-time.
| Investigate Weather Forecast AI System | Explore AI-bases system such as Nvidia’s ForeCastNet for possible integration | 2022-10-03 | 2022-10-09 | 7 | bar: Week 10/3 M to Week 10/3 S
| Preliminary feature/design notes |  | 2022-10-03 | 2022-10-16 | 14 | bar: Week 10/3 M to Week 10/10 S
| Initial UX/UI mockup |  | 2022-10-17 | 2022-10-30 | 14 | bar: Week 10/17 M to Week 11/21 S
| Basic app functionality | Build and deploy shell of app w/ working UI to then add features to | 2022-10-31 | 2022-11-27 | 28 | bar: Week 11/14 M to Week 11/21 S; Week 1/9 M to Week 1/9 S
| Panel control | Enable remote solar canopy panel control from app | 2023-01-09 | 2023-01-22 | 14 | bar: Week 1/9 M to Week 1/16 S
| Local weather conditions | Interface with local weather conditions. Try to get as localized as possible | 2023-01-09 | 2023-01-22 | 14 | bar: Week 1/16 M to Week 1/23 S
| Data collection | Collect various datapoints from connected sensors | 2023-01-23 | 2023-02-12 | 21 | bar: Week 1/30 M to Week 2/6 S
| Data visualization | Visualize collected data (graph, accessible) | 2023-02-13 | 2023-03-05 | 21 | bar: Week 2/13 M to Week 2/27 S
| Testing | Thoroughly test app to ensure functionality and compliance w/ project specs | 2023-03-06 | 2023-03-12 | 14 | bar: Week 3/6 M to Week 3/13 S
| Deployment | Deploy app to cloud computing service | 2023-03-20 | 2023-04-02 | 14 | bar: Week 3/20 M to Week 3/27 S
5 | Scale Model | Creating a scale model of the PV panel and angle controller that can be operated remotely by the software program. | bar: Week 1/9 M to Week 2/27 S
| Design a scale model | Generate schematics for scale model | 2023-01-09 | 2023-01-22 | 14 | bar: Week 1/9 M to Week 1/16 S
| Finalize Scale Model Wiring and Diagram Drawings | Review and finalize schematics, then submit to advisors along with project data sheets | 2023-01-23 | 2023-01-29 | 7 | bar: Week 1/23 M to Week 1/23 S
| Build Model | Order necessary parts, and build the model with sensors, microcontroller, panel and angle control, and software application | 2023-01-30 | 2023-02-26 | 27 | bar: Week 1/30 M to Week 2/20 S
| Connect Software Application to be used in Conjunction with Model | Connect Scale Model to Application to collect data and control panel | 2023-02-26 | 2023-03-05 | 7 | bar: Week 2/27 M to Week 2/27 S
| Model Functionality Analysis | Observe preformance of the scale model and analyze improvements, weaknesses, and strengths of model | 2023-02-26 | 2023-03-05 | 7 | bar: Week 2/27 M to Week 2/27 S
6 | Field Testing | Field-testing the developed system at a local vineyard | bar: Week 3/6 M to Week 3/27 R
| Collaborate with Canopy Team to set up system of microclimate sensors and the software application | Work with canopy team to distribute power to our system and make sure devices are compatibile with each other | 2023-03-06 | 2023-03-10 | 4 | bar: Week 3/6 M to Week 3/6 F
| Test Deployment of project | Deploy the design in the local vineyard and test the range of sensors, change of canopy angle, and connection to app | 2023-03-20 | 2023-03-25 | 5 | bar: Week 3/20 M to Week 3/20 F
| Analyze Design and Data Collected | From the data recieved from the field test, make sure model is working as intended and make adjustments to model, sensors, program, design as needed | 2023-03-23 | 2023-03-31 | 8 | bar: Week 3/20 R to Week 3/27 R
B | School Related
| Assignment 6 | Milestone, Timeline, Effort Matrix | 2022-09-30 | 2022-10-15 | 15 | bar: Week 9/26 F to Week 10/10 F
| Assignment 7 | Project Constraint Essay | 2022-10-10 | 2022-10-23 | 13 | bar: Week 10/10 M to Week 10/17 S
| Assignment 8 | Slide Presentation | 2022-10-24 | 2022-11-01 | 8 | bar: Week 10/24 M to Week 10/31 T
| Assignment 9 | Peer Review Assessment | 2022-11-02 | 2022-11-09 | 7 | bar: Week 10/31 W to Week 11/7 W
| Assignment 10 | Final Report | 2022-11-10 | 2022-12-01 | 21 | bar: Week 11/7 R to Week 11/28 R
| Assignment 11 | Advisor Assessment | 2022-11-18 | 2022-12-03 | 15 | bar: Week 11/14 F to Week 11/28 S
| CEAS Expo | The Senior Capstone Projects will be on full display at the CEAS EXPO. Graduating seniors will present their projects.